## Sep05-09
Daily Stand-up Meeting Report
Week: Sep 05 - Sep 09
Project Name: Course Scheduling Assistant
Team Name: Team D - Sigma
| Monday | Tuesday | Wednesday | Thursday | Friday
Sravya Kandepu | 1)Shared contact with other team members | 1)First Group meeting | 1) Discussed about Team roles | 1)Group Meeting- discussion on project | 1)Group Meeting- Prepared Questions for client meeting
| 2) First Group meeting | 2) Discuss about Team roles | 2)Group Meeting- discussion on project | 2)Prepare Questions for client meeting | 2) Client Meeting
| 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)No issue
Nitheesha Kotagiri | 1)Shared contact with other team members | 1)First Group meeting | 1) Discussed about Team roles | 1)Group Meeting- discussion on project | 1)Group Meeting- Prepared Questions for client meeting
| 2) First Group meeting | 2) Discuss about Team roles | 2)Group Meeting- discussion on project | 2)Prepare Questions for client meeting | 2) Client Meeting
| 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)No issue
Nikhil Kumar Vemula | 1)Shared contact with other team members | 1)First Group meeting | 1) Discussed about Team roles | 1)Group Meeting- discussion on project | 1)Group Meeting- Prepared Questions for client meeting
| 2) First Group meeting | 2) Discuss about Team roles | 2)Group Meeting- discussion on project | 2)Prepare Questions for client meeting | 2) Client Meeting
| 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)No issue
Harika Malempati | 1)Shared contact with other team members | 1)First Group meeting | 1) Discussed about Team roles | 1)Group Meeting- discussion on project | 1)Group Meeting- Prepared Questions for client meeting
| 2) First Group meeting | 2) Discuss about Team roles | 2)Group Meeting- discussion on project | 2)Prepare Questions for client meeting | 2) Client Meeting
| 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)No issue
Sanket Selokar | 1)Shared contact with other team members | 1)First Group meeting | 1) Discussed about Team roles | 1)Group Meeting- discussion on project | 1)Group Meeting- Prepared Questions for client meeting
| 2) First Group meeting | 2) Discuss about Team roles | 2)Group Meeting- discussion on project | 2)Prepare Questions for client meeting | 2) Client Meeting
| 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)No issue
Saikiran Gandam | 1)Shared contact with other team members | 1)First Group meeting | 1) Discussed about Team roles | 1)Group Meeting- discussion on project | 1)Group Meeting- Prepared Questions for client meeting
| 2) First Group meeting | 2) Discuss about Team roles | 2)Group Meeting- discussion on project | 2)Prepare Questions for client meeting | 2) Client Meeting
| 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)Who will be the main user? Professor of Administrator. | 3)No issue
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sep12-16
Daily Stand-up Meeting Report
Week: Sep 12 - Sep 16
Project Name: Course Scheduling Assistant
Team Name: Team D - Sigma
| Monday | Tuesday | Wednesday | Thursday | Friday
Sravya Kandepu | 1)Group Meeting - Discussed about changes | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Understand requirements thoroughly | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Nitheesha Kotagiri | 1)Group Meeting - Discussed about changes | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Understand requirements thoroughly | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Nikhil Kumar Vemula | 1)Group Meeting - Discussed about changes | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Understand requirements thoroughly | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Harika Malempati | 1)Group Meeting - Discussed about changes | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Understand requirements thoroughly | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Sanket Selokar | 1)Group Meeting - Discussed about changes | 1)Made blue print of User Interface | 1)Preapred for Presentation | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Understand requirements thoroughly | 2) Blue Print of UI | 2)Present PPT Presentation, Client Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Saikiran Gandam | 1)Group Meeting - Discussed about changes | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Understand requirements thoroughly | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sep 19-23
Daily Stand-up Meeting Report
Week: Sep 19 - Sep 23
Project Name: Course Scheduling Assistant
Team Name: Team D - Sigma
| Monday | Tuesday | Wednesday | Thursday | Friday
Sravya Kandepu | 1)Discussed on User Interface | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Nitheesha Kotagiri | 1)Discussed on User Interface | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Nikhil Kumar Vemula | 1)Discussed on User Interface | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Harika Malempati | 1)Discussed on User Interface | 1)Made blue print of User Interface | 1)Preapred for Presentation | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Present PPT Presentation, Client Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Sanket Selokar | 1)Discussed on User Interface | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Saikiran Gandam | 1)Discussed on User Interface | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sep 26 - 30
Daily Stand-up Meeting Report
Week: Sep 26 - Sep 30
Project Name: Course Scheduling Assistant
Team Name: Team D - Sigma
| Monday | Tuesday | Wednesday | Thursday | Friday
Sravya Kandepu | 1)Discussed on updation of User Interface | 1)Made blue print of User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI
Nitheesha Kotagiri | 1)Discussed on User Interface | 1)Discussed on User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI
Nikhil Kumar Vemula | 1)Discussed on User Interface | 1)Discussed on User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI
Harika Malempati | 1)Discussed on User Interface | 1)Discussed on User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI
Sanket Selokar | 1)Discussed on User Interface | 1)Discussed on User Interface | 1) Blue Print of UI | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Group Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI
Saikiran Gandam | 1)Discussed on User Interface | 1)Discussed on User Interface | 1)Preapred for Presentation | 1)Group Meeting | 1)Group Meeting- Prepared Questions for client meeting
| 2) Blue Print of UI | 2) Blue Print of UI | 2)Present PPT Presentation, Client Meeting | 2)Group Meeting- Prepare Questions for client meeting | 2) Client Meeting
| 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI | 3)Unclear about UI
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct 03-07
Daily Stand-up Meeting Report
Week: Oct 03 - Oct 07
Project Name: Course Scheduling Assistant
Team Name: Team D - Sigma
| Monday | Tuesday | Wednesday | Thursday | Friday
Sravya Kandepu | 1)Group Meeting - Research on Use case Diagrams | 1)Group Meeting - Worked on Use case Diagrams | 1)Preapred for Presentation | 1)Presented PPT Presentation, Client Meeting | 1)Group Meeting - Worked on Use case Diagrams
| 2)Group Meeting - Work on Use case Diagrams | 2)Group Meeting - Work on Use case Diagrams | 2)Present PPT Presentation, Client Meeting | 2)Group Meeting - Work on Use case Diagrams | 2) Prepare mid Term Presentation documents
| 3)Server side database | 3)Server side database | 3)Stucked with getting data | 3)No issue | 3)No issue
Nitheesha Kotagiri | 1)Group Meeting - Research on MockUps | 1)Group Meeting - Worked on MockUps | 1)Group Meeting - Worked on MockUps | 1) Client Meeting | 1) Prepared documents
| 2)Group Meeting - Work on MockUps | 2)Group Meeting - Work on MockUps | 2)Client Meeting | 2) Prepare documents | 2) Prepare mid Term Presentation documents
| 3)Server side database | 3)Server side database | 3)Server side database | 3)No issue | 3)No issue
Nikhil Kumar Vemula | 1)Group Meeting - Research on Use case Diagrams | 1)Group Meeting - Worked on Use case Diagrams | 1)Group Meeting - Worked on Use case Diagrams | 1) Client Meeting | 1)Preapred for Presentation
| 2)Group Meeting - Work on Use case Diagrams | 2)Group Meeting - Work on Use case Diagrams | 2)Client Meeting | 2) Prepare documents | 2)Present PPT Presentation
| 3)Server side database | 3)Server side database | 3)Server side database | 3)No issue | 3)No issue
Harika Malempati | 1)Group Meeting - Created Use case Diagrams | 1)Group Meeting - Worked on Use case Diagrams | 1)Group Meeting - Worked on Use case Diagrams | 1) Client Meeting | 1) Prepared documents
| 2)Group Meeting - Work on Use case Diagrams | 2)Group Meeting - Work on Use case Diagrams | 2)Client Meeting | 2) Prepare documents | 2) Prepare mid Term Presentation documents
| 3)Server side database | 3)Server side database | 3)Server side database | 3)No issue | 3)No issue
Sanket Selokar | 1)Group Meeting - Research on MockUps | 1)Group Meeting - Worked on MockUps | 1)Group Meeting - Worked on MockUps | 1) Client Meeting | 1) Prepared documents
| 2)Group Meeting - Work on MockUps | 2)Group Meeting - Work on MockUps | 2)Client Meeting | 2) Prepare documents | 2) Prepare mid Term Presentation documents
| 3)Server side database | 3)Server side database | 3)Server side database | 3)No issue | 3)No issue
Saikiran Gandam | 1)Group Meeting - Research on MockUps | 1)Group Meeting - Worked on MockUps | 1)Group Meeting - Worked on MockUps | 1) Client Meeting | 1) Prepared documents
| 2)Group Meeting - Work on MockUps | 2)Group Meeting - Work on MockUps | 2)Client Meeting | 2) Prepare documents | 2) Prepare mid Term Presentation documents
| 3)Server side database | 3)Server side database | 3)Server side database | 3)No issue | 3)No issue
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct 10-14
Daily Stand-up Meeting Report
Week: Oct 10 - Oct 14
Project Name: Course Scheduling Assistant
Team Name: Team D - Sigma
| Monday | Tuesday | Wednesday | Thursday | Friday
Sravya Kandepu | 1)Prepared mid Term Presentation documents | 1)Presented mid Term Presentation documents | 1)Worked on cost estimation | 1)Group meeting - for updating the documents | 1)Updated Project Management Plan
| 2)Present Mid Term Presentation | 2)Work on cost estimation | 2)Group meeting - for updating the documents | 2)Update Project Management Plan | 2) Group Meeting
| 3)Server side database | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget
Nitheesha Kotagiri | 1)Prepared mid Term Presentation documents | 1)Presented mid Term Presentation documents | 1)Worked on cost estimation | 1)Group meeting - for updating the documents | 1) Prepared documents
| 2)Present Mid Term Presentation | 2)Work on cost estimation | 2)Group meeting - for updating the documents | 2) Update Use Case Diagram | 2) Group Meeting
| 3)Server side database | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget
Nikhil Kumar Vemula | 1)Prepared mid Term Presentation documents | 1)Presented mid Term Presentation documents | 1)Worked on cost estimation | 1)Group meeting - for updating the documents | 1)Preapred for Presentation
| 2)Present Mid Term Presentation | 2)Work on cost estimation | 2)Group meeting - for updating the documents | 2) Update Use Case Diagram | 2) Group Meeting
| 3)Server side database | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget
Harika Malempati | 1)Prepared mid Term Presentation documents | 1)Presented mid Term Presentation documents | 1)Worked on cost estimation | 1)Group meeting - for updating the documents | 1) Prepared documents
| 2)Present Mid Term Presentation | 2)Work on cost estimation | 2)Group meeting - for updating the documents | 2) Update Use Case Diagram | 2) Group Meeting
| 3)Server side database | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget
Sanket Selokar | 1)Prepared mid Term Presentation documents | 1)Presented mid Term Presentation documents | 1)Worked on cost estimation | 1)Group meeting - for updating the documents | 1)Updated Project Management Plan
| 2)Present Mid Term Presentation | 2)Work on cost estimation | 2)Group meeting - for updating the documents | 2)Update Project Management Plan | 2) Group Meeting
| 3)Server side database | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget
Saikiran Gandam | 1)Prepared mid Term Presentation documents | 1)Presented mid Term Presentation documents | 1)Worked on cost estimation | 1)Group meeting - for updating the documents | 1)Updated Project Management Plan
| 2)Present Mid Term Presentation | 2)Work on cost estimation | 2)Group meeting - for updating the documents | 2)Update Project Management Plan | 2) Group Meeting
| 3)Server side database | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct 17-21
Daily Stand-up Meeting Report
Week: Oct 17 - Oct 21
Project Name: Course Scheduling Assistant
Team Name: Team D - Sigma
| Monday | Tuesday | Wednesday | Thursday | Friday
Sravya Kandepu | 1)Group Meeting - discussed about Data Flow Diagrams | 1)Group Meeting - Worked on Use case Diagrams | 1)Group Meeting - Brainstormed about database connectivity | 1)Looked at all the functional requirements | 1)Looked at all the functional requirements
| 2)Group Meeting - Work on Use case Diagrams | 2)Group Meeting - Brainstorming about database connectivity | 2)Look at all the functional requirements | 2)Look at all the functional requirements | 2)Group Meeting - Issue discussion
| 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)No issue | 3)No issue
Nitheesha Kotagiri | 1)Group Meeting - discussed about Use case Diagrams | 1)Group Meeting - Worked on MockUps | 1)Group Meeting - Brainstormed about database connectivity | 1)Looked at all the faculty page related requirements | 1)Looked at all the faculty page related requirements
| 2)Group Meeting - Work on MockUps | 2)Group Meeting - Brainstorming about database connectivity | 2)Look at all the faculty page related requirements | 2)Look at all the faculty page related requirements | 2)Group Meeting - Issue discussion
| 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)No issue | 3)No issue
Nikhil Kumar Vemula | 1)Group Meeting - discussed about Use case Diagrams | 1)Group Meeting - Worked on Use case Diagrams | 1)Group Meeting - Brainstormed about database connectivity | 1)Looked at all the faculty page related requirements | 1)Looked at all the faculty page related requirements
| 2)Group Meeting - Work on Use case Diagrams | 2)Group Meeting - Brainstorming about database connectivity | 2)Look at all the faculty page related requirements | 2)Look at all the faculty page related requirements | 2)Group Meeting - Issue discussion
| 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)No issue | 3)No issue
Harika Malempati | 1)Group Meeting - discussed about Use case Diagrams | 1)Group Meeting - Worked on Use case Diagrams | 1)Group Meeting - Brainstormed about database connectivity | 1)Looked at all the faculty page related requirements | 1)Looked at all the faculty page related requirements
| 2)Group Meeting - Work on Use case Diagrams | 2)Group Meeting - Brainstorming about database connectivity | 2)Look at all the faculty page related requirements | 2)Look at all the faculty page related requirements | 2)Group Meeting - Issue discussion
| 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)No issue | 3)No issue
Sanket Selokar | 1)Group Meeting - discussed about Data Flow Diagrams | 1)Group Meeting - Worked on MockUps | 1)Group Meeting - Brainstormed about database connectivity | 1)Looked at all the functional requirements | 1)Looked at all the functional requirements
| 2)Group Meeting - Work on MockUps | 2)Group Meeting - Brainstorming about database connectivity | 2)Look at all the functional requirements | 2)Look at all the functional requirements | 2)Group Meeting - Issue discussion
| 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)No issue | 3)No issue
Saikiran Gandam | 1)Group Meeting - discussed about Data Flow Diagrams | 1)Group Meeting - Worked on MockUps | 1)Group Meeting - Brainstormed about database connectivity | 1)Looked at all the functional requirements | 1)Looked at all the functional requirements
| 2)Group Meeting - Work on MockUps | 2)Group Meeting - Brainstorming about database connectivity | 2)Look at all the functional requirements | 2) Prepare documents | 2)Group Meeting - Issue discussion
| 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)Approximate calculation of project budget | 3)No issue | 3)No issue
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct 24-28
Daily Stand-up Meeting Report
Week: Oct 24 - Oct 28
Project Name: Course Scheduling Assistant
Team Name: Team D - Sigma
| Monday | Tuesday | Wednesday | Thursday | Friday
Sravya Kandepu | 1)Group Meeting - Issue discussion | 1)Group Meeting | 1)Group Meeting - Worked on Use case Diagrams | 1) Client Meeting | 1)Group Meeting - Worked on Login related requirements
| 2)Group Meeting | 2)Group Meeting - Work on Use case Diagrams | 2)Client Meeting | 2)Group Meeting - Work on Login related requirements | 2) Research on Test plan
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Nitheesha Kotagiri | 1)Group Meeting - Research on MockUps | 1)Group Meeting | 1)Group Meeting - Worked on issue and requirements documents | 1) Client Meeting | 1)Group Meeting - Worked on Login related requirements
| 2)Group Meeting | 2)Group Meeting - Work on issue and requirements documents | 2)Client Meeting | 2)Group Meeting - Work on Login related requirements | 2) Research on Test plan
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Nikhil Kumar Vemula | 1)Group Meeting - Research on Use case Diagrams | 1)Group Meeting | 1)Group Meeting - Worked on Use case Diagrams | 1) Client Meeting | 1)Group Meeting - Worked on Login related requirements
| 2)Group Meeting | 2)Group Meeting - Work on Use case Diagrams | 2)Client Meeting | 2)Group Meeting - Work on Login related requirements | 2)Update Use Case diagram
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Harika Malempati | 1)Group Meeting - Created Use case Diagrams | 1)Group Meeting | 1)Group Meeting - Worked on Use case Diagrams | 1) Client Meeting | 1) Group Meeting - Worked on Admin authority related requirements
| 2)Group Meeting | 2)Group Meeting - Work on Use case Diagrams | 2)Client Meeting | 2)Group Meeting - Work on Admin authority related requirements | 2)Update Use Case diagram
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Sanket Selokar | 1)Group Meeting - Research on MockUps | 1)Group Meeting | 1)Group Meeting - Worked on issue and requirements documents | 1) Client Meeting | 1) Group Meeting - Worked on Admin authority related requirements
| 2)Group Meeting | 2)Group Meeting - Work on issue and requirements documents | 2)Client Meeting | 2)Group Meeting - Work on Admin authority related requirements | 2) Create Data Flow Diagram
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Saikiran Gandam | 1)Group Meeting - Research on MockUps | 1)Group Meeting | 1)Group Meeting - Worked on issue and requirements documents | 1) Client Meeting | 1) Group Meeting - Worked on Admin authority related requirements
| 2)Group Meeting | 2)Group Meeting - Work on issue and requirements documents | 2)Client Meeting | 2)Group Meeting - Work on Admin authority related requirements | 2) Create Data Flow Diagram
| 3)No issue | 3)No issue | 3)No issue | 3)No issue | 3)No issue
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Oct 31 - Nov 4
Daily Stand-up Meeting Report
Week: Oct 31 - Nov 4
Project Name: Course Scheduling Assistant
Team Name: Team D - Sigma
| Monday | Tuesday | Wednesday | Thursday | Friday
Sravya Kandepu | 1)Researched on Test plan | 1)Group Meeting - Worked on Requirements documents | 1)Prepared for client Meeting | 1)Client Meeting | 1)Group Meeting
| 2)Prepare requirements documents for client meeting | 2)Prepare for client Meeting | 2)Client Meeting - Walk client throughout the project | 2)Group Meeting | 2)Group Meeting - Updation of documents
| 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file
Nitheesha Kotagiri | 1)Researched on Test plan | 1)Group Meeting - Worked on Requirements documents | 1)Prepared for client Meeting | 1) Client Meeting | 1)Group Meeting
| 2)Prepare requirements documents for client meeting | 2)Prepare for client Meeting | 2)Client Meeting - Walk client throughout the project | 2)Group Meeting | 2)Group Meeting - Updation of documents
| 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file
Nikhil Kumar Vemula | 1)Updated Use Case diagram | 1)Group Meeting - Worked on Requirements documents | 1)Prepared for client Meeting | 1) Client Meeting | 1)Group Meeting
| 2)Prepare requirements documents for client meeting | 2)Prepare for client Meeting | 2)Client Meeting - Walk client throughout the project | 2)Group Meeting | 2)Group Meeting - Updation of documents
| 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file
Harika Malempati | 1)Updated Use Case diagram | 1)Group Meeting - Worked on Requirements documents | 1)Prepared for client Meeting | 1) Client Meeting | 1)Group Meeting
| 2)Prepare requirements documents for client meeting | 2)Prepare for client Meeting | 2)Client Meeting - Walk client throughout the project | 2)Group Meeting | 2)Group Meeting - Updation of documents
| 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file
Sanket Selokar | 1)Created Data Flow Diagram | 1)Group Meeting - Worked on Requirements documents | 1)Prepared for client Meeting | 1) Client Meeting | 1)Group Meeting
| 2)Prepare requirements documents for client meeting | 2)Prepare for client Meeting | 2)Client Meeting - Walk client throughout the project | 2)Group Meeting | 2)Group Meeting - Updation of documents
| 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file
Saikiran Gandam | 1)Created Data Flow Diagram | 1)Group Meeting - Worked on Requirements documents | 1)Prepared for client Meeting | 1) Client Meeting | 1)Group Meeting
| 2)Prepare requirements documents for client meeting | 2)Prepare for client Meeting | 2)Client Meeting - Walk client throughout the project | 2)Group Meeting | 2)Group Meeting - Updation of documents
| 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file | 3) Login encrypted file
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Nov 7-11
Daily Stand-up Meeting Report
Week: Nov 07 - Nov 11
Project Name: Course Scheduling Assistant
Team Name: Team D - Sigma
| Monday | Tuesday | Wednesday | Thursday | Friday
Sravya Kandepu | 1)Updated documents | 1)Collected requirements document from client. | 1)Group Meeting - made changes on functional requirements document | 1)Group Meeting - made changes on functional requirements document | 1)Group Meeting - Found out the questions about requirements for client
| 2)Collection of requirements document from client. | 2)Group Meeting - make changes on functional requirements document | 2)Group Meeting - make changes on functional requirements document | 2)Group Meeting - Find out the questions about requirements for client | 2) Client Meeting
| 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3)No issue
Nitheesha Kotagiri | 1)Updated documents | 1)Collected requirements document from client. | 1)Group Meeting - made changes on Use case Diagrams | 1)Group Meeting - made changes on Use case Diagrams | 1)Group Meeting - Found out the questions about requirements for client
| 2)Collection of requirements document from client. | 2)Group Meeting - make changes on Use case Diagrams | 2)Group Meeting - make changes on Use case Diagrams | 2)Group Meeting - Find out the questions about requirements for client | 2) Client Meeting
| 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3)No issue
Nikhil Kumar Vemula | 1)Updated documents | 1)Collected requirements document from client. | 1)Group Meeting - made changes on Use case Diagrams | 1)Group Meeting - made changes on Use case Diagrams | 1)Group Meeting - Found out the questions about requirements for client
| 2)Collection of requirements document from client. | 2)Group Meeting - make changes on Use case Diagrams | 2)Group Meeting - make changes on Use case Diagrams | 2)Group Meeting - Find out the questions about requirements for client | 2) Client Meeting
| 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3)No issue
Harika Malempati | 1)Updated documents | 1)Collected requirements document from client. | 1)Group Meeting - made changes on Use case Diagrams | 1)Group Meeting - made changes on Use case Diagrams | 1)Group Meeting - Found out the questions about requirements for client
| 2)Collection of requirements document from client. | 2)Group Meeting - make changes on Use case Diagrams | 2)Group Meeting - make changes on Use case Diagrams | 2)Group Meeting - Find out the questions about requirements for client | 2) Client Meeting
| 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3)No issue
Sanket Selokar | 1)Updated documents | 1)Collected requirements document from client. | 1)Group Meeting - made changes on functional requirements document | 1)Group Meeting - made changes on functional requirements document | 1)Group Meeting - Found out the questions about requirements for client
| 2)Collection of requirements document from client. | 2)Group Meeting - make changes on functional requirements document | 2)Group Meeting - make changes on functional requirements document | 2)Group Meeting - Find out the questions about requirements for client | 2) Client Meeting
| 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3)No issue
Saikiran Gandam | 1)Updated documents | 1)Collected requirements document from client. | 1)Group Meeting - made changes on functional requirements document | 1)Group Meeting - made changes on functional requirements document | 1)Group Meeting - Found out the questions about requirements for client
| 2)Collection of requirements document from client. | 2)Group Meeting - make changes on functional requirements document | 2)Group Meeting - make changes on functional requirements document | 2)Group Meeting - Find out the questions about requirements for client | 2) Client Meeting
| 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3) Encryption while login | 3)No issue
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?